## Assessment
Prevention through Design (PtD) Hazard Risk Assessment
Date: |  | Project: |  |  |  |  | Review Phase | Requirements & Specifications
Assessed By: |  | Sub-system:
Identifier | Potential Hazard Description | Life Cycle Stage | Who is at risk? | What is at risk? | Pre-Mitigation Severity | Pre-Mitigation Probability | Pre-Mitigation Risk Score | Mitigations | Post-Mitigation Severity | Post-Mitigation Probability | Post-Mitigation Risk Score | Mitigation Action | Status of Implementation | Comments
Fabrication

## Examples
Prevention through Design (PtD) Hazard Risk Assessment
Date: |  | Project: |  |  |  |  | Review Phase | Requirements & Specifications
Assessed By: |  | Sub-system:
Identifier | Potential Hazard Description | Life Cycle Stage | Who is at risk? | What is at risk? | Pre-Mitigation Severity | Pre-Mitigation Probability | Pre-Mitigation Risk Score | Mitigations | Post-Mitigation Severity | Post-Mitigation Probability | Post-Mitigation Risk Score | Mitigation Action | Status of Implementation | Comments
| Overexposure to radiation from machine operations | Operations | Personnel on access in beamline enclosure |  | Critical | A - Almost Certain | 1 - Critical | Global requirement to supply a radiation safety interlock system. Technical specification for system to be compliant with FRCM Chapter 10. | Critical | E - Rare | 3 - Moderate | Integrate into Design | In Process
| Injury or fatality due to catastrophic failure of a cryomodule | Operations | Personnel on access in beamline enclosure |  | Critical | C - Possible | 1 - Critical | General Functional Requirement to abide by all FESHM and FRCM requirements. Specific pressure and cryogenic safety chapters from the FESHM are referenced in the FRS. | Critical | E - Rare | 3 - Moderate | Integrate into QA Plan | Implemented
| Insufficient space for radiological frisking equipment limits emergency egress path | Operations | Personnel on Access |  | High | C - Possible | 2 - Serious | Conventional Facilities Technical Specification updated to define necessary space for enclosure frisking equipment | High | E - Rare | 4 - Minor | Update Specifications and Interfaces | In Process
| Strain injury during LCW pump installation / replacement | Multiple | Contractors and Maintenance personnel |  | High | B - Likely | 1 - Critical | Conventional Facilities Technical Specification to design in an A-Frame lifting fixture rated for 1 ton to facilitate pump installation / removal | Low | D - Unlikely | 4 - Minor | Integrate into Design | Implemented
| Environmental impact from antifreeze in cooling water system | Disposal or Recycling |  | Cooling ponds and waters of the state | Low | C - Possible | 3 - Moderate | Technical Specification to use propylene glycol for an antifreeze in cooling water system | Minimal | C - Possible | 4 - Minor | No Action Required | Not Implemented | Determined antifreeze in cooling water is unnecessary

## Hazard Severity Matrix
Fermilab QAM 12030TA Table 1
HAZARD SEVERITY
SEVERITY | PEOPLE | ENVIRONMENT | COMPLIANCE | PROPERTY | PROCESS/PROJECT
CRITICAL | Multiple deaths from injury or illness; multiple cases of injuries involving permanent disability; or chronic irreversible illnesses. | Permanent loss of a public resource (e.g. drinking water, air, stream, or river). | Willful disregard for the rules and regulations. | Loss of multiple facilities or program components; (>$5,000,000 total cost*) | Total breakdown identified resulting in loss/shut down of a process or project.
HIGH | One death from injury or illness; one case of injury involving permanent disability; or chronic irreversible illnesses. | Long-term loss of a public resource (e.g., drinking water, air, stream, or river). | Major noncompliance that exposes the Lab to significant potential fines and penalties. | Loss of a facility or critical program component; (>$5,000,000 total cost*) | Major breakdown identified resulting in the failure to attain the budget, schedule, key performance indicators or customer expectations.
MEDIUM | Injuries or temporary, reversible illnesses resulting in hospitalization of a variable but limited period of disability. | Seriously impair the functioning of a public resource. | Significant noncompliance that requires reporting to DOE or other authorities. | Major property damage or critical program component; ($1,000,000 - $5,000,000 total cost*) | Significant compromise to the attainment of the budget, schedule, key performance indicators or customer expectations which exposes process/project to potential failure if gap cannot be immediately resolved.
LOW | Injuries or temporary, reversible illnesses not resulting in hospitalization with lost time. | Isolated and minor, but measurable, impact(s) on some component(s) of a public resource. | Programmatic noncompliance with the Lab's Work Smart set. | Minor property damage or critical program component; ($50,000 - $1,000,000 total cost*) | Minor breakdown or gap identified which does not result in significant compromise to the attainment of the budget, schedule, key performance indicators or customer expectations; gaps can be resolved.
MINIMAL | Injuries or temporary illnesses requiring only minor supportive treatment and no lost time. | No measurable impact on component(s) of a public resource | Specific instance of a noncompliance with the Lab's Work Smart set. | Standard property damage or critical program component; (<$50,000 total cost*) | Minor gaps identified which do not compromise the attainment of the budget, schedule, key performance indicators or customer expectations; gaps can easily be resolved.
* total cost = total dollar value including parts, labor, contingency plans, etc. that is necessary to repair/replace property or program component.

## Probability
Fermilab QAM 12030TA Table 2
MISHAP PROBABILITY TABLE
PROBABILITY | DESCRIPTION
A - Almost Certain | Could occur annually
B - Likely | Could occur once in two years
C - Possible | Occurring not more than once in ten years
D - Unlikely | Occurring not more than once in thirty years
E - Rare | Occurring not more than once in one hundred years.

## Risk Assessment Actions
Risk Assessment Codes and Actions
1 - Very High | Unacceptable. Operation not permissible. Immediate action necessary.
2 - High | Mitagation action(s) to be given a high priority.
3 - Moderate | Mitagation action(s) to be taken at an appropriate time. Can be considered an acceptable risk.
4 - Low | Mitagation action(s) discretionary.
5 - Negligible | No action necessary.
;

## Look-up Tables
Life Cycle Stage | Severity | Probability |  |  | Risk Matrix |  |  |  | Mitigation Status | Mitigation Status | Review Phase
|  |  |  | A - Almost Certain | B - Likely | C - Possible | D - Unlikely | E - Rare
Fabrication | Critical | A - Almost Certain | Critical | 1 - Critical | 1 - Critical | 1 - Critical | 2 - Serious | 3 - Moderate | Int. into Design | Not Implemented | Requirements & Specifications
Installation | High | B - Likely | High | 1 - Critical | 1 - Critical | 2 - Serious | 3 - Moderate | 4 - Minor | Int. into QA Plan | In Process | Conceptual Design
Commissioning | Medium | C - Possible | Medium | 1 - Critical | 2 - Serious | 3 - Moderate | 3 - Moderate | 4 - Minor | Int. into Specs and Interfaces | Implemented | Preliminary Design
Operations | Low | D - Unlikely | Low | 2 - Serious | 3 - Moderate | 3 - Moderate | 4 - Minor | 5 - Negligible | Int. into Admin Proc. and PPE |  | Final Design
Equipment Shutdown | Minimal | E - Rare | Minimal | 3 - Moderate | 4 - Minor | 4 - Minor | 5 - Negligible | 5 - Negligible | No Action Required |  | Manufacturing Readiness
Maintenance | [10 empty] | Procurement Readiness
Trouble-shooting | [10 empty] | System Acceptance
Repairs/Replacement | [10 empty] | Transportation Readiness
Decommissioning | [10 empty] | Installation Readiness
Disposal or Recycling | [10 empty] | Operational Readiness
Shipping
Inspection
Testing
Multiple